## Road Projects
ROAD PROJECTS
|  |  | CONSTRUCTION |  | FISCAL YEAR ($000)
CIE # | PROJECT | NOTES | COMMENCE | COMPLETE | 2005-2006 | 2006-2007 | 2007-2008 | 2008-2009 | 2009-2010 | TOTAL
60001A | Collier Blvd US 41 to Golden Gate Canal | 06D/R, 07R, 10C/I |  |  | 4863 | 4000 |  |  | 37070 | 45933
60005 | Goodlett Frank Pine Ridge Rd to GG Pkwy | 06C/I/LD, 07C/LS |  |  | 17850 | 1019 |  |  |  | 18869
60006 | Golden Gate Pkwy Overpass | 06C/I/LS, 07C |  |  | 32843 | 383 |  |  |  | 33226
60018 | Immokalee Rd Collier Blvd to 43rd | 06C/I, 07R/C/I, 09LS |  |  | 15880 | 3493 |  | 2448 |  | 21821
60091 | Santa Barbara Blvd / Polly Rattlesnake to Davis | 06D/R, 08R, 10C/I |  |  | 8844 |  | 2865 |  | 38667 | 50376
60101 | County Barn Rd Davis Rd to CR 864 | 06R/LD |  |  | 5640 |  |  |  |  | 5640
60166 | Logan Blvd Pine Ridge to Immokalee Rd | 06R/LD, 07R |  |  | 1656 | 345 |  |  |  | 2001
60168 | Vanderbilt Beach Rd Collier Blvd - Wilson | 06D/R, 07 - 09/R |  |  | 3118 | 8000 | 12200 | 11921 |  | 35239
60169 | Rattlesnake Hammock Rd Polly Av to Collier Blvd | 06C/I, 08LS |  |  | 29828 |  | 565 |  |  | 30393
62081A | Santa Barbara Blvd Ph 1 CST/Ph 1 ROW Davis to N. of Golden Gate Pkwy | 06D/R, 07R, 10C/I |  |  | 11822 | 66217 |  |  |  | 78039
62081B | Santa Barbara Blvd Ph 2 ROW Copperleaf to Green | 07R, 08R |  |  |  | 1972 | 2000 |  |  | 3972
63051 | Vanderbilt Beach Rd Airport Rd to Collier Blvd | 06R/C/I/LD, 07LS |  |  | 36386 | 1407 |  |  |  | 37793
65061 | Collier Blvd Immokalee Rd to GG Blvd | 06R/LD, 09LD/LS |  |  | 47036 |  |  | 850 |  | 47886
66042 | Immokalee Rd US 41 to I-75 | 06R/C/I/LD, 09LS |  |  | 32342 |  |  | 1035 |  | 33377
68056 | Collier Blvd GG Blvd to Pine Ridge Rd | 06D/R, 10C/I, 11C,I |  |  | 7800 |  |  |  | 12495 | 20295
66045 | Immokalee Road I-75 to Collier Blvd | 06D/C/I, 09LS |  |  | 24042 |  |  | 1193 |  | 25235
60044A | Oil Well Rd Immokalee Rd to Everglades Blvd | 06R, 07R, 10C/I |  |  | 2200 | 4131 |  |  | 54272 | 60603
60044B | Oil Well Rd Everlgades Blvd to DeSoto Rd | 06R, 07R, 11C/I |  |  | 3000 | 2978 |  |  |  | 5978
60044C | Oil Well Rd DeSoto to Camp Keais Rd | [8 empty] | 0
62024 | Green Blvd Livingston to Santa Barbara Blvd | 06S |  |  | 155 |  |  |  |  | 155
60040 | Golden Gate Blvd Wilson to E. of Everglades | 06D, 07R, 08R, 09R, 10C/I |  |  | 3400 | 3600 | 3000 | 17224 | 51286 | 78510
60038 | SR 82 Lee Co Line to SR 29 | 06D |  |  | 500 |  |  |  |  | 500
60065 | Randall Rlvd | 06D, 07R, 08R, 09R, 10C/I |  |  | 756 | 2000 | 5619 | 2638 |  | 11013
TBD | Wilson Blvd GG Blvd to Immokalee Rd | 08D, 09R, 10R |  |  |  |  | 1500 | 2000 | 1000 | 4500
60134 | Goodlette-Frank Rd Pine Ridge Rd to Vanderbilt Beach Rd | 06R/LS |  |  | 1344 |  |  |  |  | 1344
60027 | Golden Gate Pkwy Landscape | 06R/LS |  |  | 1299 |  |  |  |  | 1299
62071 | Livingston Rd Vanderbilt Beach Rd to Immokalee Rd | 06LS |  |  | 344 |  |  |  |  | 344
66060 | I-75 Interchange at Everglades Rd | 06S |  |  | 750 |  |  |  |  | 750
60162 | Tropicana Bridge | 06C |  |  | 1500 |  |  |  |  | 1500
60176 | Davis Blvd Lighting | 06C |  |  | 715 |  |  |  |  | 715
TBD | Immokalee Rd I-75 Loop | 07 - 09C, 09 - 13LP |  |  |  | 18540 |  | 2040 | 2040 | 22620
60138A | Advanced Construction | 07C |  |  |  | 43011 |  |  |  | 43011
60138B | Advanced Landscape | 08 - 11LS |  |  |  |  | 1399 | 2209 | 620 | 4228
| Contingency |  |  |  |  | 27735 |  |  | 23051 | 50786
SBTL | Roads Subtotals |  |  |  | 295913 | 188831 | 29148 | 43558 | 220501 | 777951
Sbttl | Base Operations & Maintenance |  |  |  | 23303 | 7350 | 5550 | 7300 | 10300 | 53803
Sbttl | Enhanced Operations & Maintenance |  |  |  | 1292 | 723 | 600 | 600 | 600 | 3815
60003 | Collector Rds / Minor Arterial Rds |  |  |  | 8601 | 6782 | 5219 | 5480 | 5754 | 31836
60171 | Advanced ROW |  |  |  | 1725 | 100 | 100 | 909 | 700 | 3534
| Debt Service Payments |  |  |  | 14538 | 14614 | 14580 | 14582 | 14580 | 72894
| ROADS TOTALS |  |  |  | 345372 | 218400 | 55197 | 72429 | 252435 | 943833
Key:
S = Study D = Design
M = Mitigation C = Construction
AC = Advanced Construction
I = Inspection
R = Right of Way
LS = Landscape
LD = Landscape Design
LP = SIB Loan Payback
NOTE: Collier County has adopted a two-year Concurrency Management System. Figures provided for years three, four and five of this Schedule of Capital Improvements are not part of the Concurrency Management System but are subject to proportionate share. Years provided for production in six through ten of this Schedule of Capital Improvements are estimated and do not include cost estimates due to large costs increases we have been experiencing the last two years. The years shown are probable based on the revenue stream but exact costs cannot be determined at this time and this data does not constitute a long term concurrency system.

## Park Projects
PARK PROJECTS
|  |  | CONSTRUCTION |  | FISCAL YEAR ($000)
CIE # | PROJECT | NOTES | COMMENCE | COMPLETE | 2005-2006 | 2006-2007 | 2007-2008 | 2008-2009 | 2009-2010 | TOTAL
80001 | Community Park Lands | Acquisition | Continuous |  |  |  |  | 7000 | 5000 | 12000
80002 | Regional Park Lands | Acquisition | Continuous |  |  |  | 1200 |  |  | 1200
80003 | Shell Island Road/Rookery Bay Canoe | Ramp Improvements | 10/08 | 09/10 |  |  |  | 1600 |  | 1600
80122 | Manatee | Community Park Phase-In | 04/02 | 09/10 |  |  |  |  | 8000 | 8000
80014 | Eagle Lakes | Water Play, Landscaping, Walks | 02/03 | 05/06 | 370 | 525 |  |  |  | 895
80039 | Orange Tree Park | Development | 10/07 | 09/12 |  | 350 |  |  |  | 350
80004 | Elementary School | Field Upgrades, 10 ac. | 10/07 | 09/08 |  | 400 |  |  |  | 400
80005 | Caribbean Gardens/GRGP | Regional Park Phase-In | [5 empty] | 2000 |  | 2000
80006 | Golden Gate Estates | Phase 1 | 10/09 | 09/12 | [5 empty] | 0
80170-1 | Airport Park, Immokalee | WCs, Shelter, Enhanced Parking | 10/06 | 09/08 | [5 empty] | 0
80007 | Sugden | Building | 10/06 | 09/08 |  |  | 1000 |  |  | 1000
80024 | Goodland - Margood | Community Park Phase-In | 10/05 | 09/10 | 300 |  | 825 |  |  | 1125
80611 | Goodland Boat Park | Phase 1 | 10/05 | 01/09 |  | 1300 |  | 1700 |  | 3000
34207 | East Naples Community Park | Expansion | 11/03 | 09/06 | 950 |  |  |  |  | 950
80057 | Caxambas Park | New Dock | 10/05 | 09/08 | 100 | 100 |  |  |  | 200
80040 | Keewaydin Boat Shuttle | Install Dock / Boat Shuttle | 10/06 | 09/09 |  |  | 400 | 4000 |  | 4400
80058 | Vanderbilt Inn Beach Access |  | 10/05 | 09/07 |  |  |  | 500 |  | 500
90295 | Vanderbilt Parking Garage |  | 05/04 | 01/06 | 8000 |  |  |  |  | 8000
| Refurbishments - General | Ongoing |  |  | 950 | 1100 | 600 | 1100 | 1100 | 4850
80033/5 | Refurb - Playground Replacements | VTCP & South Park (06) |  |  | 150 | 100 | 100 | 100 | 100 | 550
80121 | Refurb - GG Comm Park | Ball Field Fences / Pavilion |  | 10/05 | 100 |  |  |  |  | 100
80170-2 | Refurb - Immok Airport Park | [5 empty] | 500 |  |  | 500
| PARKS TOTALS |  |  |  | 10920 | 3875 | 4625 | 18000 | 14200 | 51620
NOTE: Collier County has adopted a two-year Concurrency Management System. Figures provided for years three, four and five of this Schedule of Capital Improvements are not part of the Concurrency Management System but are subject to proportionate share. Figures provided for years six through ten of this Schedule of Capital Improvements are estimates of revenues versus project costs but do not constitute a long term concurrency system.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Stormwater Mgmt Projects
STORMWATER MANAGEMENT PROJECTS
|  |  | CONSTRUCTION |  | FISCAL YEAR ($000)
CIE # | PROJECT | NOTES | COMMENCE | COMPLETE | 2005-2006 | 2006-2007 | 2007-2008 | 2008-2009 | 2009-2010 | TOTAL
511011 | Lely Area | Stormwater Improvement Project |  | 06 - 09D/C/R, 10C/R, 11 - 13C | 497 | 7996 | 11617 | 11886 | 10778 | 42774
510185 | Gordon River | Water Quality Park |  | 06D-07D/C | 674 | 10420 |  |  |  | 11094
518031 | Gateway Triangle | Improvements |  | 06 - 08D/C/R, 09D/C, 10C | 249 | 1565 | 500 | 1000 | 1750 | 5064
TBD | Belle Meade Stormwater Impr | Stormwater Improvements |  | 08D - 09C/R, 10 - 14C |  |  | 100 | 400 | 400 | 900
| STORMWATER MANAGEMENT TOTALS |  |  |  | 1420 | 19981 | 12217 | 13286 | 12928 | 59832
Key:
| S = Study | LS = Landscape
| D = Design | C = Construction
| M = Mitigation | I = Inspection
R = Right of Way
NOTE: Collier County has adopted a two-year Concurrency Management System. Figures provided for years three, four and five of this Schedule of Capital Improvements are not part of the Concurrency Management System but are subject to proportionate share. Figures provided for years six through ten of this Schedule of Capital Improvements are estimates of revenues versus project costs but do not constitute a long term concurrency system.

## Potable Water Projects
POTABLE WATER PROJECTS
|  |  | CONSTRUCTION |  | FISCAL YEAR ($000)
CIE # | PROJECT | NOTES | COMMENCE | COMPLETE | 2005-2006 | 2006-2007 | 2007-2008 | 2008-2009 | 2009-2010 | TOTAL
| TOTAL POTABLE WATER* |  |  |  | 76253 | 85170 | 32395 | 93370 | 61180 | 348368
NOTE: Collier County has adopted a two-year Concurrency Management System. Figures provided for years three, four and five of this Schedule of Capital Improvements are not part of the Concurrency Management System but are subject to proportionate share. Figures provided for years six through ten of this Schedule of Capital Improvements are estimates of revenues versus project costs but do not constitute a long term concurrency system.
*NOTE: For a complete list see Water Table 8.2 that is a separate attachment to this document. These projects are listed separately and incorporated into the CIE by reference.

## Solid Waste Projects
SOLID WASTE PROJECTS
|  |  | CONSTRUCTION |  | FISCAL YEAR ($000)
CIE # | PROJECT | NOTES | COMMENCE | COMPLETE | 2005-2006 | 2006-2007 | 2007-2008 | 2008-2009 | 2009-2010 | TOTAL
TBD | Naples Landfill Expansion | Cell A2 - Phase 1 | 2006 | 2006 | 3254 |  |  |  |  | 3254
TBD | Naples Landfill Expansion | Cell A2 - Phase 2 | 2007 | 2007 |  | 675 |  |  |  | 675
TBD | Naples Landfill Expansion | Cells A3 - Phases 1 & 2 | 2009 | 2009 | 0 |  |  | 1534 |  | 1534
| SOLID WASTE TOTALS |  |  |  | 3254 | 675 | 0 | 1534 | 0 | 5463
NOTE: Collier County has adopted a two-year Concurrency Management System. Figures provided for years three, four and five of this Schedule of Capital Improvements are not part of the Concurrency Management System but are subject to proportionate share. Figures provided for years six through ten of this Schedule of Capital Improvements are estimates of revenues versus project costs but do not constitute a long term concurrency system.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## SEWER PROJECTS
SEWER PROJECTS
|  |  | CONSTRUCTION |  | FISCAL YEAR ($000)
CIE # | PROJECT | NOTES | COMMENCE | COMPLETE | 2005-2006 | 2006-2007 | 2007-2008 | 2008-2009 | 2009-2010 | TOTAL
| SEWER TOTALS* |  |  |  | 40593 | 43654 | 58485 | 68460 | 89960 | 301152
NOTE: Collier County has adopted a two-year Concurrency Management System. Figures provided for years three, four and five of this Schedule of Capital Improvements are not part of the Concurrency Management System but are subject to proportionate share. Figures provided for years six through ten of this Schedule of Capital Improvements are estimates of revenues versus project costs but do not constitute a long term concurrency system.
*NOTE: For a complete list see Wastewater Table 8.2 that is a separate attachment to this document. These projects are listed separately and incorporated into the CIE by reference.

## Costs and Revenues Recap
The table below itemizes the types of public facilities and the sources of revenue. The center column
contains the 5-Year amount of facility revenues. The right column is a calculation of expenses versus
revenues for each type of public facility. All deficits are accumulated as a subtotal. The subtotal
deficit is the source of additional revenue utilized by Collier County to fund the deficit in order to
maintain the levels of service standards as referenced in the Capital Improvement Element.
ROAD PROJECTS |  |  |  |  | 943833000
Less Revenues:
| Gas Tax Revenue |  | 110587000
| Impact Fee Revenue, including COA Revenue |  | 212257000
| Carry Forward, including Bonds |  | 381155185
| Grants/Reimbursements |  | 79939000
| DCAs/Advanced Reimbursements |  | 0
| Ave Maria |  | 28722000
| General Fund |  | 135191000
| Transfers |  | 815
| Revenue Reserve |  | -4019000 |  | 943833000
|  |  |  | Balance | 0
PARKS & RECREATION PROJECTS |  |  |  |  | 51620000
Less Revenues:
| Impact Fee Revenue (bonds, cash & loans) |  | 32527000
| TDC Funds, including Vanderbilt Garage |  | 12500000
| Ad Valorem |  | 6000000
| Grants |  | 593000
51620000
|  |  |  | Balance | 0
STORMWATER & DRAINAGE PROJECTS |  |  |  |  | 59832000
Less Revenues:
| Ad Valorem |  | 34965000
(FY06-10 from Stormwater Utility -
@ 0.15 Mills per year - est.)
| Grants/Reimbursements |  | 13692000
| Big Cypress Basin/SWFMD |  | 11175000 |  | 59832000
|  |  |  | Balance | 0
POTABLE WATER PROJECTS |  |  |  |  | 348368000
Less Revenues:
| Bonds and Commercial Paper |  | 156766000
| State Rotating Funds |  | 64796000
| Impact Fees |  | 81867000
| User Rates |  | 44939000
348368000
|  |  |  | Balance | 0
SEWER PROJECTS |  |  |  |  | 301152000
Less Revenues:
| Bonds and Commercial Paper |  | 41257000
| State Rotating Funds |  | 126183000
| Impact Fees |  | 82516000
| User Rates |  | 51196000 |  | 301152000
|  |  |  | Balance | 0
SOLID WASTE PROJECTS |  |  |  |  | 5463000
Less Revenues:
| User Tipping Fees |  | 5463000
5463000
|  |  |  | Balance | 0
TOTAL PROJECTS |  | 1721081000 |  | TOTAL REVENUE SOURCES | 1710268000