## Sheet1
Naples - Park Shore - Vanderbilt Beach Renourishment
Total Project Cost Summary
Charges through 10/4/2004 | 1700000
Sand Placement and Mobilization | 18477000
Reef
Monitoring | 840000
Construction | 1000000
Design | 203000
Pre-Construction Survey | 65000
Post Construction Survey | 88000
Construction Management | 360000
Design Charges from 10/04 through 7/05 | 200000
Contingency | 250000
Totals | 23183000
Original Project Budget | 19233000
Difference | 3950000
Reconciliation
Reduce scope to 625K CY from 673K CY | Included in $2M Bid/Price reduction
Reduce Screening at Dredges | Included in $2M Bid/Price reduction
Reduce mobilization costs | Included in $2M Bid/Price reduction
Clarify pay templates | Included in $2M Bid/Price reduction
FDEP funding to $6,458K from $2,700K | 3758000
Funding by Pelican Bay | 840000
4th Cent Impact & 3 yr repay of 194 Funds | ++++++++
Spread Major Renourishment over 10 years | ++++++++
Added Caxambas Pass and Clam Pass | ---------------
Changed timing of Catastrophe Reserve | ++++++++